## Website Proposal
WEBSITE PROPOSAL TIMELINE
PROJECT DETAILS
Week | DATE | MILESTONE | Description | POSITION
#1 | 2016-03-14 | Project Start | Design + Code: Preliminary Planning | 25
#2 | 2016-03-21 | Milestone 1 | Design + Code: Strategic Vision & Direction | 10
#3 | 2016-03-28 | Milestone 2 | Design + Code: Research & Discovery | -10
#4 | 2016-04-04 | Milestone 3 | Design + Code: Brand/Key Messaging | 15
#5 | 2016-04-11 | Milestone 4 | Design + Code: Content Strategy & Development | -15
#6 | 2016-04-18 | Milestone 5 | Design + Code: Information Architecture | 15
#7 | 2016-04-25 | Milestone 6 | Design + Code: Concept/Design Development | -15
#8 | 2016-05-02 | Milestone 7 | Design + Code: Technical Development/Programming | 15
#9 | 2016-05-16 | Milestone 8 | Design + Code: Content & Site Building | -20
#10 | 2016-05-23 | Milestone 9 | Design + Code:Beta Testing/Soft Launch | 20
#11 | 2016-05-30 | Milestone 10 | Design + Code: Official Launch | -15
#12 | 2016-06-05 | Milestone 11 | Design + Code: Post Launch | 15
Project End
Website Project Timeline: